## Sheet1
ID # | Type | Priority | Description | Created On | Created By | ETA | Closed On | Comments
1 | Bug | 2-Med | GetOff functionality depends on network naming, domain suffixes. We need to have a more reliable way of telling machines to do the get off command. | 2013-04-09 | Aaron
2 | Bug | 1-High | If a node can't talk to the database at the time it finishes a job, its status never changes back to IDLE, and the job is not marked as FINISHED. | 2013-04-09 | Aaron |  |  | Currently, each occurrence requires manual correction.
3 | Request | 3-Low | Make it possible to submit a batch of jobs. Different .ma files, but same project folder, frame range, priority, etc. | 2013-04-11 | Aaron
4 | Request | 3-Low | Use Google Docs for issue tracking | 2013-04-11 | Aaron
5 | Maintenance | 3-Low | Remove or repurpose the recent tasks tab in FarmView | 2013-04-11 | Aaron |  |  | The recent tasks tab is useful because it shows Project, Frame range, and because it allows the user to see an exploded view of what tasks are in the Ready queue. I feel that this tab should be changed to better serve the needs it is fulfilling. A lot of the info shown in the Recent Tasks tab is redundant with the Job List and could be merged into that tab.